## Toolkit for Organizing Wheelchair Basketball Events

Introduction

This toolkit is designed to support organizations, federations, and clubs in planning, organizing, and delivering wheelchair basketball events. It incorporates best practices from the POWER project and provides a step-by-step guide to ensure inclusivity, accessibility, and high-quality event execution.

### Event Planning & Management Guide

Intro into project planning that provides a comprehensive framework for planning and executing POWER project events, ensuring effective coordination, clear timelines, and high-quality participant experiences.

#### 1.1 Planning Timeline

- 12 months before: Define objectives, secure funding, identify venues.

- 9 months before: Confirm partnerships, begin promotion, recruit core team.

- 6 months before: Open registration for teams, confirm referees and technical staff.

- 3 months before: Conduct site visits, finalize logistics.

- 1 month before: Volunteer training, finalize event program.

- Event week: Set up venue, run technical checks.

#### 1.2 Budgeting and Finance

- Budget template includes:

  - Venue rental

  - Equipment and wheelchair maintenance

  - Staff and volunteer expenses

  - Marketing and promotion

  - Contingency funds (10%)

#### 1.3 Risk Management

- Develop a risk register covering:

  - Accessibility issues

  - Medical emergencies

  - Weather (for outdoor events)

  - Transportation delays

### Promotion and Visibility

Section outlines strategies for increasing the project’s reach, including social media campaigns, press releases, and stakeholder engagement to boost awareness and inclusivity.

#### 2.1 Communication Strategy

- Target audiences: athletes, spectators, sponsors, media.

- Channels: social media, local press, radio, community outreach.

#### 2.2 Promotional Materials

- Templates for flyers, posters, and press releases.

- Suggested hashtags: #WheelchairBasketball, #InclusionThroughSport

#### 2.3 Stakeholder Engagement

- Organize stakeholder events to secure support from local authorities, sponsors, and disability organizations.

### Operational & Technical Guidelines

This chapter details the essential procedures and best practices for smooth operations, focusing on logistics, venue setup, and technical requirements for each activity.

#### 3.1 Roles and Responsibilities

- Event Director: Overall coordination

- Technical Delegate: Compliance with IWBF rules

- Volunteer Coordinator: Recruitment and training

#### 3.2 Equipment Checklist

- Approved sports wheelchairs

- Court markings and accessible facilities

- Spare parts and repair station

#### 3.3 Transportation and Logistics

- Ensure accessible transport for athletes and spectators

- Provide clear signage and maps of the venue

### Inclusive Participation Toolkit

This toolkit offers resources and guidance for fostering inclusive environments, including accessibility tips, cultural sensitivity, and engaging participants with diverse needs.

#### 4.1 Volunteer Engagement

- Develop training modules on disability awareness

- Assign roles for accessibility support (e.g., assisting athletes)

#### 4.2 Athlete Recruitment

- Partner with rehabilitation centers and disability organizations

- Run open days and demo sessions to attract new participants

#### 4.3 Diversity and Gender Equality

- Ensure balanced representation in athletes, coaches, and officials

### Monitoring & Evaluation Tools

Methodologies and templates for tracking project progress, measuring impact, and ensuring continuous improvement through feedback and data collection

#### 5.1 Key Performance Indicators (KPIs)

- Number of participating teams and athletes

- Audience reach (in-person and online)

- Media coverage

- Stakeholder satisfaction

#### 5.2 Feedback Mechanisms

- Pre- and post-event surveys for participants and stakeholders

- Debrief sessions with organizing team

### Templates and Resources (Annex)

A collection of ready-to-use documents such as agendas, registration forms, feedback surveys, and communication templates to support project implementation.

- Sample event timeline

- Budget template

- Risk assessment form

- Volunteer training manual outline

- Marketing and press release templates

### Conclusion

This toolkit serves as a practical guide for developing and promoting wheelchair basketball at all levels. It emphasizes inclusivity, sustainability, and international collaboration to ensure the growth of the sport and its positive impact on communities.

### ANNEX

#### Sample Event Timeline (POWER Project)

| Task | Responsible Party | Start Date | End Date |
| --- | --- | --- | --- |
| Kick-off Meeting | HSKUK | 01/09/2024 | 30/09/2024 |
| Educational Programme (Training) | University of Niš, Partners | 01/10/2024 | 31/01/2025 |
| Stakeholder Engagement Event #1 | All Partners | 15/02/2025 | 15/02/2025 |
| Stakeholder Engagement Event #2 | All Partners | 15/03/2025 | 15/03/2025 |
| Website Launch | HSKUK | 01/10/2024 | 31/10/2024 |
| Final Meeting | HSKUK | 01/08/2025 | 31/08/2025 |
| Evaluation & Reporting | All Partners | 01/08/2025 | 31/08/2025 |

#### Budget Template

| Category | Estimated Cost (€) | Notes |
| --- | --- | --- |
| Venue Rental | 5,000 | For training and engagement events |
| Travel & Accommodation | 10,000 | Partner representatives and trainers |
| Promotional Materials | 3,000 | Flyers, banners, booklets |
| Trainer & Speaker Fees | 8,000 | For expert-led sessions |
| Volunteer Stipends | 2,500 | Travel and meals |
| Miscellaneous | 1,500 | Contingency |
| Total | 30,000 |  |

#### Risk Assessment Form

| Risk Description | Likelihood | Impact | Mitigation Plan |
| --- | --- | --- | --- |
| Low participant attendance | Medium | High | Targeted marketing, early outreach |
| Venue unavailability | Low | High | Secure bookings early, have backups |
| Volunteer no-shows | Medium | Medium | Maintain standby list of volunteers |
| Budget overrun | Medium | High | Monthly financial monitoring |
| IT/technical issues during online events | High | Medium | Test systems in advance, have support |

#### Volunteer Training Manual Outline

- Introduction to POWER Project

  - Objectives

  - Partners and stakeholders

- Volunteer Roles & Responsibilities

  - Event support

  - Participant assistance

  - Promotion and outreach

- Communication & Teamwork

  - Working with diverse groups

  - Conflict resolution basics

- Health, Safety & Accessibility

  - Emergency procedures

  - Supporting participants with disabilities

- Event Day Procedures

  - Check-in process

  - Scheduling and assignments

- Evaluation and Feedback

  - Post-event survey

#### Marketing and Press Release Templates

Marketing Template (Social Media Post)

Empowering Wheelchair Basketball: Building Capacity and Sharing Knowledge Across Borders!

Join us in creating a more inclusive Europe through sport.  Next Event: [Event Name] – [Date] Location: [Venue]

Learn more: [Website URL] #Inclusion #WheelchairBasketball #ErasmusSport #POWERProject

#### Press Release Template

FOR IMMEDIATE RELEASE

Empowering Wheelchair Basketball Across Europe: The POWER Project Launches

Zagreb, [Date] – The Croatian Wheelchair Basketball Federation (HSKUK) and partners across Europe have launched the POWER project to foster inclusion and enhance wheelchair basketball.

The 12-month initiative will train over 50 coaches and leaders, host stakeholder events, and launch educational resources. Supported by Erasmus+, POWER builds capacity and creates lasting impact in Croatia, Serbia, and North Macedonia.

For more information, visit [Website URL] or contact [Contact Name, Email].